Q:-  Answer the following question

What is Network Planning, and why is it important in project management?

- What is the difference between PERT and CPM in project analysis?

Q:-  Given the following project activities and their precedence relationships

| Activity | Predecessor | Duration (days) |
| --- | --- | --- |
| A | — | 3 |
| B | A | 5 |
| C | A | 4 |
| D | B, C | 6 |

Using PERT, calculate the expected time for each activity

Q :-

| Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) |
| --- | --- | --- | --- |
| A | 2 | 4 | 6 |
| B | 3 | 5 | 9 |
| C | 1 | 2 | 3 |

Q:-  Can you explain your graduation project, including its main idea, objectives, methodology, implementation process, results, and possible future improvements?   Q: A project has the following data at the end of week 4:
Planned Value (PV) = $80,000
Earned Value (EV) = $70,000
Actual Cost (AC) = $90,000
Budget at Completion (BAC) = $250,000

Required:
1. Calculate CV, SV, CPI, and SPI.
2. Interpret the project performance in terms of cost and schedule.
3. Determine whether the project is over or under budget.

Q:-  Answer the following question

- Explain the concept of the Critical Path. How is it determined in a network diagram?

- What are Activities and Events in network planning? Explain the difference with an example.

Q:-  Given the following project activities and their precedence relationships

| Activity | Predecessor | Duration (days) |
| --- | --- | --- |
| A | — | 4 |
| B | A | 6 |
| C | A | 5 |
| D | B, C | 7 |

Using PERT, calculate the expected time for each activity

| Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) |
| --- | --- | --- | --- |
| A | 3 | 5 | 7 |
| B | 2 | 6 | 10 |
| C | 1 | 3 | 5 |

Q    Can you explain your graduation project, including its main idea, objectives, methodology, implementation process, results, and possible future improvements?

Q: A project has the following data at the end of week 8

Planned Value (PV) = $200,000
Earned Value (EV) = $220,000
Actual Cost (AC) = $210,000
Budget at Completion (BAC) = $400,000
Required:
1. Calculate CV, SV, CPI, and SPI.
2. Interpret the project performance in terms of cost and schedule.
3. Determine whether the project is over or under budget.

Q

How can the total project duration be calculated using a network diagram? Explain the main steps.

- What are Early Time and Late Time? Why are they important in project scheduling?

Q Given the following project activities and their precedence relationships

| Activity | Predecessor | Duration (days) |
| --- | --- | --- |
| A | — | 2 |
| B | A | 8 |
| C | A | 3 |
| D | B, C | 5 |

Using PERT, calculate the expected time for each activity

Q :-

| Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) |
| --- | --- | --- | --- |
| A | 3 | 5 | 9 |
| B | 2 | 6 | 8 |
| C | 1 | 4 | 7 |

Q:-  Can you explain your graduation project, including its main idea, objectives, methodology, implementation process, results, and possible future improvements?  (10 marks )

Q: A project has the following data at the end of week 5:
Planned Value (PV) = $150,000
Earned Value (EV) = $120,000
Actual Cost (AC) = $140,000
Budget at Completion (BAC) = $350,000

Required:
1. Calculate CV, SV, CPI, and SPI.
2. Interpret the project performance in terms of cost and schedule.
3. Determine whether the project is over or under budget.